## Sheet1
Requirement ID | Description | Story Points | Priority | Sprint Number (Estimated) | Completed
1 | As a company I want this hosted on a vps on the cloud | 1 | 1 | 1
2 | As a company I want the data to be stored on the cloud in a database | 1 | 1 | 1
3 | Design and Logo | 1 | 1 | 1
4 | Home Page User Interface | 3 | 3 | 1
5 | Login Page User Interface | 3 | 3 | 1
6 | Signup Page User Interface | 3 | 3 | 1
7 | Home Page Backend | 3 | 2 | 1
8 | Login Page Backend | 3 | 2 | 1
10 | Signup Page Backend | 3 | 2 | 1
11 | As a company, I want my network traffic to be secure. We need to use nginx to route traffic and handle tls/ssl. | 1 | 2 | 2
12 | create a session manager library to track logged in users. | 2 | 2 | 1
13 | Dashboard User Interface | 3 | 3 | 2
14 | Dashboard Backend | 3 | 2 | 2
15 | Setup Go Backend | 3 | 1 | 1
16 | Set up CI/CD pipeline | 2 | 2 | 1
17 | Create crypto payment listener | 21 | 2 | 3
18 | Create crypto smart contract to handle payment | 21 | 2 | 2
19 | Create Invoice library | 21 | 2 | 2
20 | Payment widget for merchant websites. | 21 | 2 | 3
21 | Create different user roles for merchants (Admin, Developer) | 5 | 2 | 2
22 | Create user management Dashboard UI | 5 | 2 | 2
23 | Create user management dashboard backend | 5 | 2 | 2
24 | Create UI to add crypto wallet to merchant account | 21 | 3 | 3
25 | Create backend to handle adding of crypto wallet to account | 21 | 3 | 3
26 | Seed database with test account for development | 2 | 2 | 2
27 | Create root.css to handle light/dark mode | 1 | 1 | 1